COMP6011 Advanced Artificial Intelligence Research Topics

Research Progress Document

# 1. Project Overview

This document records the research progress undertaken for COMP6011 Task 2. The task required investigating, comparing, and validating Large Language Model (LLM) approaches for suicide risk detection from conversational transcripts. The output is a research and technical report addressed to an executive team and clinical advisors, covering literature review, benchmarking, proof-of-concept implementation, and ethical analysis.

The core research question was: can zero-shot NLI-based classifiers reliably classify suicide risk from multi-turn dialogue transcripts into five ordinal categories — attempt, behavior, ideation, indicator, and safe — without domain-specific fine-tuning?

# 2. Weekly Research Timeline

## Week 1-2: Problem Understanding and Task Scoping

Activities completed:

- Read and analysed the full Task 2 specification document carefully

- Identified the five key deliverables: literature review, benchmarking, proof-of-concept, ethics discussion, and implementation plan

- Reviewed the provided 10-case dataset to understand the label schema and clinical context

- Noted the critical constraint that private conversations must not be sent to public AI APIs

- Identified the Columbia Suicide Severity Rating Scale (C-SSRS) as the standard clinical framework for this domain

## Week 3-4: Literature Review and Background Research

Activities completed:

- Searched Google Scholar, PubMed, arXiv, and ACL Anthology for relevant papers on LLM-based mental health classification

- Identified key benchmark datasets: Reddit r/SuicideWatch, CLPsych 2019, Chinese social media mental health corpora

- Read and noted key papers including Lewis et al. (2020) on BART, He et al. (2021) on DeBERTa, Ji et al. (2022) on MentalBERT

- Reviewed Zhou et al. (2025) evaluating Claude, GPT-4, Mistral, and LLaMA on C-SSRS Reddit benchmark

- Read Xu et al. (2023) Mental-LLM paper comparing LLMs on mental health prediction tasks

- Reviewed WHO (2021) global suicide statistics to ground the clinical context

- Constructed a taxonomy of NLP approaches: lexicon-based, traditional ML, BERT-variants, frontier LLMs

## Week 5-6: Benchmarking Dataset Selection and Planning

Activities completed:

- Identified two publicly accessible external datasets for benchmarking evaluation

- Dataset 1: Suicide and Depression Detection (Komati, 2022) — binary Reddit posts, accessible via HuggingFace without login

- Dataset 2: Mental Health Text Classification (Mukherjee, 2025) — four-class mental health dataset, also accessible via HuggingFace

- Confirmed both datasets load automatically in Google Colab using load_dataset() without manual download

- Planned label mapping strategy from binary/multi-class labels to the five-class ordinal scheme

- Documented mapping decisions and rationale: suicide -> ideation (conservative), non-suicide -> safe, Depression/Anxiety -> indicator

## Week 7-8: Proof-of-Concept Implementation

Activities completed:

- Set up Google Colab environment with T4 GPU runtime

- Installed required libraries: transformers, torch, scikit-learn, datasets, pandas, matplotlib, seaborn

- Implemented Method A: BART-large-MNLI zero-shot NLI pipeline

- Designed natural language hypotheses for all five risk categories for Method A

- Implemented Method B: DeBERTa-v3-small NLI zero-shot pipeline

- Designed separate hypothesis set for Method B to avoid hypothesis anchoring

- Implemented transcript truncation function: retain first and last 200 words for transcripts exceeding 400 words

- Ran both methods on all 10 provided cases

- Computed accuracy, Macro F1, precision, recall, Cohen's Kappa, and MAE for both methods

- Identified 100% false negative rate on high-risk cases as the critical clinical safety finding

## Week 9: Benchmarking Implementation

Activities completed:

- Added benchmarking cells to existing notebook — no new notebook created

- Loaded Dataset 1 (Komati 2022) from HuggingFace, sampled 75 posts per class (150 total)

- Loaded Dataset 2 (Mukherjee 2025) from HuggingFace, sampled 50 posts per class (200 total)

- Applied label mapping and verified class distributions before inference

- Ran BART and DeBERTa on both external datasets and recorded all results

- Constructed full comparison table including published results from Zhou et al. (2025) and published RoBERTa fine-tuned results

- Generated benchmarking bar charts and confusion matrix

- Noted key finding: 30-60 percentage point gap between own zero-shot models and published frontier LLMs

## Week 10-11: Report Writing and Finalisation

Activities completed:

- Drafted all report sections in order: Abstract, Introduction, Literature Review, Benchmarking, Methodology, AI Ethics, Discussion, Conclusion

- Ensured 10 provided cases used only in Methodology section and not in Benchmarking

- Added privacy constraint discussion to Methodology section covering local deployment, AES-256 encryption, TLS 1.3, RBAC, audit logging

- Addressed all eight Australian AI Ethics Principles with specific rather than generic discussion

- Computed carbon footprint using ML CO2 Impact calculator (Lacoste et al., 2019)

- Aligned project with SDG 3, SDG 9, and SDG 10

- Verified all 12 references have working, clickable URLs or DOIs

- Generated system architecture diagram (Figure 2) and literature taxonomy diagram (Figure 1)

- Finalised notebook with all PoC and benchmarking cells in sequence

# 3. Methods Investigated

## 3.1 Methods Considered but Not Selected

During the literature review phase, several alternative approaches were considered before finalising the two candidate methods:

- GPT-4 API (zero-shot): Strong published performance (72.8% accuracy on C-SSRS Reddit benchmark) but rejected on data privacy grounds — routing patient mental health transcripts through the OpenAI API would violate the Australian Privacy Act 1988

- Claude API (zero-shot): Highest published performance (73.3% accuracy) but rejected for the same privacy reasons as GPT-4

- MentalBERT (fine-tuned): Strong domain-specific performance but requires labelled clinical training data not available for this proof-of-concept

- RoBERTa (fine-tuned): Highest benchmark accuracy (97.4%) but again requires supervised fine-tuning data; included as upper-bound reference in benchmarking only

- Llama-3 via Ollama (local): Ideal production approach — fully local, no API calls, privacy-preserving — but resource requirements exceeded available Colab GPU memory for reliable inference within time constraints

## 3.2 Methods Selected and Rationale

| Method | Model | Rationale | Limitation |
| --- | --- | --- | --- |
| Method A | BART-large-MNLI | 400M params, broad semantic coverage, strong NLI pre-training, open-weight | Encoder-decoder, not decoder-based LLM |
| Method B | DeBERTa-v3-small | Compact 180M params, efficient, NLI fine-tuned, suitable for constrained environments | Small model, limited semantic range |

# 4. Datasets Used

| Dataset | Source | Labels | Sample Used | Mapped To |
| --- | --- | --- | --- | --- |
| 10-case PoC set (Chen et al., 2026) | Zenodo | 5-class ordinal | All 10 cases | Used directly (Methodology only) |
| Suicide & Depression Detection (Komati, 2022) | HuggingFace | Binary | 150 posts | ideation / safe |
| Mental Health Text Classification (Mukherjee, 2025) | HuggingFace | 4-class | 200 posts | ideation / indicator / safe |
| Reddit C-SSRS (Zhou et al., 2025) | Published paper | 7-point C-SSRS | Reference only | Literature comparison |

# 5. Key Results Summary

## 5.1 Proof-of-Concept Results (10 Cases)

| Metric | Method A (BART) | Method B (DeBERTa) | Clinical Threshold | Verdict |
| --- | --- | --- | --- | --- |
| Accuracy | 20% | 10% | >85% | Both fail |
| Macro F1 | 0.080 | 0.044 | >0.80 | Both fail |
| High-risk FN rate | 100% | 100% | 0% | Both fail (critical) |
| Cohen's Kappa | Low | Very low | >0.60 | Both fail |

## 5.2 Benchmarking Results (External Datasets)

| Model | Dataset | Accuracy | Macro F1 | Source |
| --- | --- | --- | --- | --- |
| BART (Method A) | Komati 2022 | 12.0% | 0.142 | This work |
| DeBERTa (Method B) | Komati 2022 | 43.3% | 0.342 | This work |
| BART (Method A) | Mukherjee 2025 | 25.0% | 0.133 | This work |
| DeBERTa (Method B) | Mukherjee 2025 | 5.5% | 0.064 | This work |
| Claude 3.5 (zero-shot) | Reddit C-SSRS | 73.3% | 0.751 | Zhou et al. (2025) |
| GPT-4 (zero-shot) | Reddit C-SSRS | 72.8% | 0.738 | Zhou et al. (2025) |
| RoBERTa (fine-tuned) | Reddit SuicideWatch | 97.4% | — | J.Med.Sys (2024) |

# 6. Key Research Findings

- Zero-shot encoder-based NLI classifiers (BART, DeBERTa) are insufficient for clinical suicide risk detection — both produced a 100% false negative rate on high-risk cases

- The performance gap between own zero-shot models and published frontier LLMs (Claude 3.5, GPT-4) is 30 to 60 percentage points, confirming that model scale and decoder architecture matter significantly

- Neither model generalises consistently across datasets — DeBERTa outperformed BART on Dataset 1 but collapsed on Dataset 2, indicating sensitivity to label distribution and domain

- Fine-tuned models (RoBERTa at 97.4% accuracy) substantially outperform zero-shot approaches, confirming that domain-specific training data is a prerequisite for clinical deployment

- Data privacy is a hard architectural constraint: no patient mental health conversation may be routed through a public API. Local deployment using Llama-3 or Mistral-7B via Ollama/vLLM is the only viable production approach

- Method A (BART-large-MNLI) is recommended as the preferred foundation based on superior proof-of-concept metrics and greater architectural capacity for downstream fine-tuning

# 7. Privacy and Deployment Decisions

A critical design decision throughout this project was the approach to data privacy. The following constraints were identified early in the research process and governed all implementation choices:

- All inference was performed locally on Google Colab T4 GPU using open-weight models downloaded from HuggingFace

- No transcript or post content was transmitted to any external API (OpenAI, Anthropic, or otherwise)

- Models used (BART, DeBERTa) are open-weight and fully self-contained — no network calls during inference

- External datasets were loaded via the HuggingFace datasets library, which downloads models locally before inference begins

- The production deployment recommendation explicitly requires locally hosted LLMs (Llama-3, Mistral-7B) or institutionally managed private cloud

# 8. Literature Reviewed

The following papers were read and considered during this project. All 12 final references include a working URL or DOI verified before submission.

- Chen et al. (2026) — Human-AI-Dialogue-Suicide-Risk-Dataset (Zenodo dataset used for PoC)

- He et al. (2021) — DeBERTaV3: Improving DeBERTa using ELECTRA-style pre-training

- Ji et al. (2021) — Suicidal ideation detection: A review of machine learning methods

- Ji et al. (2022) — MentalBERT: Publicly available pretrained language models for mental healthcare

- Komati (2022) — Suicide and Depression Detection dataset (Kaggle/HuggingFace)

- Lacoste et al. (2019) — Quantifying the carbon emissions of machine learning

- Lewis et al. (2020) — BART: Denoising sequence-to-sequence pre-training

- Mukherjee (2025) — Mental Health Text Classification dataset (HuggingFace)

- Posner et al. (2011) — The Columbia-Suicide Severity Rating Scale

- WHO (2021) — Suicide worldwide in 2019: Global health estimates

- Xu et al. (2023) — Mental-LLM: Leveraging large language models for mental health prediction

- Zhou et al. (2025) — Evaluating LLM reasoning for suicide screening with C-SSRS

# 9. Challenges Encountered and How They Were Resolved

| Challenge | Impact | Resolution |
| --- | --- | --- |
| AIMH/SWMH dataset on HuggingFace was gated (login required) | Could not load Dataset 2 automatically in Colab | Replaced with Mukherjee (2025) dataset which is fully open and login-free |
| 10-case dataset initially used in Benchmarking section incorrectly | Structural mismatch with assignment requirements | Moved 10-case results to Methodology only; created separate Benchmarking section using external datasets |
| Both models showed 100% false negative rate on high-risk cases | Core finding rather than failure — expected without fine-tuning | Reframed as primary clinical safety finding and used to motivate production recommendations |
| Label mapping from binary/multi-class to 5-class scheme | Risk of misrepresenting dataset labels | Documented conservative mapping decisions explicitly as limitations in report and notebook |
| Performance inconsistency across the two external datasets | DeBERTa outperformed BART on D1 but collapsed on D2 | Analysed as domain sensitivity finding — strengthens the argument for fine-tuning |